## SCHEDULE
Schedule for SeaTac Standards Development
Weeks
|  | Task |  |  | Responsible Party | Prior To |  | Deadline | Done
[6 empty] | Completion |  | Date
| Research Comparable Agency's Standards |  |  | Janet Mayer |  | 72 | Fri | 2016-10-28 | ü
| Develop Template |  |  | Janet Mayer |  | 69 | Fri | 2016-11-18 | ü
| Template Review |  |  | Distribution List (Standards Committee) |  | 66 | Fri | 2016-12-09 | ü
| Template Review Comments Due |  |  | Distribution List (Standards Committee) |  | 65 | Fri | 2016-12-16 | ü
| Meeting to Discuss Template |  |  | Standards Committee |  | 65 | Fri | 2016-12-16 | ü
| Template Revision |  |  | Janet Mayer |  | 65 | Fri | 2016-12-16 | ü
| Revised Template Review |  |  | Distribution List (Standards Committee) |  | 64 | Fri | 2016-12-23 | ü
| Revised Template Review Comments Due |  |  | Distribution List (Standards Committee) |  | 62 | Wed | 2017-01-04 | ü
| Meeting to Approve Template and to Look Ahead to Chapter 1 |  |  | Standards Committee |  | 62 | Thur | 2017-01-05 | ü
| Begin Chapter 1 |  |  | Janet Mayer |  | 62 | Fri | 2017-01-06 | ü
| T&PW Meeting - Discuss Standards Development |  |  | T&PW Committee |  | 60 | Thur | 2017-01-19 | ü
| Begin Forming Stakeholders Group |  |  | Standards Committee |  | 60 | Fri | 2017-01-20 | ü
| Chapter 1 Review |  |  | Distribution List (Standards Committee) |  | 59 | Thur | 2017-01-26 | ü
| Chapter 1 Review Comments Due |  |  | Distribution List (Standards Committee) |  | 58 | Wed | 2017-02-01 | ü
| Stakeholders Group Kickoff |  |  | Stakeholders Group |  | 58 | Wed | 2017-02-01 | ü
| Meeting to Discuss Chapter 1 |  |  | Standards Committee |  | 58 | Thur | 2017-02-02 | ü
| Begin Chapter 1 Revision |  |  | Janet Mayer |  | 58 | Fri | 2017-02-03 | ü
| Revised Chapter 1 Review |  |  | Distribution List (Standards Committee) |  | 56 | Thur | 2017-02-16 | ü
| Revised Chapter 1 Review Comments Due |  |  | Distribution List (Standards Committee) |  | 55 | Wed | 2017-02-21 | ü
| Stakeholders Meeting to Discuss Chapter 1 |  |  | Stakeholders Group |  | 55 | Thu | 2017-02-22 | ü
| Meeting to Approve Chapter 1 and Look Ahead to Chapter 2 |  |  | Standards Committee |  | 55 | Thur | 2017-02-23 | ü
| Begin Chapter 2 |  |  | Janet Mayer |  | 55 | Fri | 2017-02-24 | ü
| Chapter 2 Review |  |  | Distribution List (Standards Committee) |  | 53 | Thur | 2017-03-09
| Chapter 2 Review Comments Due |  |  | Distribution List (Standards Committee) |  | 52 | Wed | 2017-03-15
| Stakeholders Meeting to Discuss Chapter 2 |  |  | Stakeholders Group |  | 52 | Wed | 2017-03-15
| Meeting to Discuss Chapter 2 |  |  | Standards Committee |  | 52 | Fri | 2017-03-17
| Begin Chapter 2 Revision |  |  | Janet Mayer |  | 52 | Fri | 2017-03-17
| Revised Chapter 2 Review |  |  | Distribution List (Standards Committee) |  | 50 | Thur | 2017-03-30
| Revised Chapter 2 Review Comments Due |  |  | Distribution List (Standards Committee) |  | 49 | Wed | 2017-04-05
| Meeting to Approve Chapter 2 and Look Ahead to Chapter 3 |  |  | Standards Committee |  | 49 | Thur | 2017-04-06
| Begin Chapter 3 |  |  | Janet Mayer |  | 49 | Fri | 2017-04-07
| Chapter 3 Review |  |  | Distribution List (Standards Committee) |  | 47 | Thur | 2017-04-20
| Chapter 3 Review Comments Due |  |  | Distribution List (Standards Committee) |  | 46 | Wed | 2017-04-26
| Stakeholders Meeting to Discuss Chapter 3 |  |  | Stakeholders Group |  | 46 | Wed | 2017-04-26
| Meeting to Discuss Chapter 3 |  |  | Standards Committee |  | 46 | Thur | 2017-04-27
| Begin Chapter 3 Revision |  |  | Janet Mayer |  | 46 | Fri | 2017-04-28
| Revised Chapter 3 Review |  |  | Distribution List (Standards Committee) |  | 44 | Thur | 2017-05-11
| Revised Chapter 3 Review Comments Due |  |  | Distribution List (Standards Committee) |  | 43 | Wed | 2017-05-17
| Meeting to Approve Chapter 3 and Look Ahead to Chapter 4 |  |  | Standards Committee |  | 43 | Thur | 2017-05-18
| Begin Chapter 4 |  |  | Janet Mayer |  | 43 | Fri | 2017-05-19
| Chapter 4 Review |  |  | Distribution List (Standards Committee) |  | 41 | Thur | 2017-06-01
| Chapter 4 Review Comments Due |  |  | Distribution List (Standards Committee) |  | 40 | Wed | 2017-06-07
| Stakeholders Meeting to Discuss Chapter 4 |  |  | Stakeholders Group |  | 40 | Wed | 2017-06-07
| Meeting to Discuss Chapter 4 |  |  | Standards Committee |  | 40 | Thur | 2017-06-08
| Begin Chapter 4 Revision |  |  | Janet Mayer |  | 40 | Fri | 2017-06-09
| Revised Chapter 4 Review |  |  | Distribution List (Standards Committee) |  | 38 | Thur | 2017-06-22
| Revised Chapter 4 Review Comments Due |  |  | Distribution List (Standards Committee) |  | 37 | Wed | 2017-06-28
| Meeting to Approve Chapter 4 and Look Ahead to Chapter 5 |  |  | Standards Committee |  | 37 | Thur | 2017-06-29
| Begin Chapter 5 |  |  | Janet Mayer |  | 37 | Fri | 2017-06-30
| Chapter 5 Review |  |  | Distribution List (Standards Committee) |  | 35 | Thur | 2017-07-13
| Chapter 5 Review Comments Due |  |  | Distribution List (Standards Committee) |  | 34 | Wed | 2017-07-19
| Stakeholders Meeting to Discuss Chapter 5 |  |  | Stakeholders Group |  | 34 | Wed | 2017-07-19
| Meeting to Discuss Chapter 5 |  |  | Standards Committee |  | 34 | Thur | 2017-07-20
| Begin Chapter 5 Revision |  |  | Janet Mayer |  | 34 | Fri | 2017-07-21
| Revised Chapter 5 Review |  |  | Distribution List (Standards Committee) |  | 32 | Thur | 2017-08-03
| Revised Chapter 5 Review Comments Due |  |  | Distribution List (Standards Committee) |  | 31 | Wed | 2017-08-09
| Meeting to Approve Chapter 5 and Look Ahead to Chapter 6 |  |  | Standards Committee |  | 31 | Thur | 2017-08-10
| Begin Chapter 6 |  |  | Janet Mayer |  | 31 | Fri | 2017-08-11
| Chapter 6 Review |  |  | Distribution List (Standards Committee) |  | 29 | Thur | 2017-08-24
| Chapter 6 Review Comments Due |  |  | Distribution List (Standards Committee) |  | 28 | Wed | 2017-08-30
| Stakeholders Meeting to Discuss Chapter 6 |  |  | Stakeholders Group |  | 28 | Wed | 2017-08-30
| Meeting to Discuss Chapter 6 |  |  | Standards Committee |  | 28 | Thur | 2017-08-31
| Begin Chapter 6 Revision |  |  | Janet Mayer |  | 28 | Fri | 2017-09-01
| Revised Chapter 6 Review |  |  | Distribution List (Standards Committee) |  | 26 | Thur | 2017-09-14
| Revised Chapter 6 Review Comments Due |  |  | Distribution List (Standards Committee) |  | 25 | Wed | 2017-09-20
| Meeting to Approve Chapter 6 and Look Ahead to Chapter 7 |  |  | Standards Committee |  | 25 | Thur | 2017-09-21
| Begin Chapter 7 |  |  | Janet Mayer |  | 25 | Fri | 2017-09-22
| Chapter 7 Review |  |  | Distribution List (Standards Committee) |  | 23 | Thur | 2017-10-05
| Chapter 7 Review Comments Due |  |  | Distribution List (Standards Committee) |  | 22 | Wed | 2017-10-11
| Stakeholders Meeting to Discuss Chapter 7 |  |  | Stakeholders Group |  | 22 | Wed | 2017-10-11
| Meeting to Discuss Chapter 7 |  |  | Standards Committee |  | 22 | Thur | 2017-10-12
| Begin Chapter 7 Revision |  |  | Janet Mayer |  | 22 | Fri | 2017-10-13
| Revised Chapter 7 Review |  |  | Distribution List (Standards Committee) |  | 20 | Thur | 2017-10-26
| Revised Chapter 7 Review Comments Due |  |  | Distribution List (Standards Committee) |  | 19 | Wed | 2017-11-01
| Meeting to Approve Chapter 7 and Look Ahead to Chapter 8 |  |  | Standards Committee |  | 19 | Thur | 2017-11-02
| Begin Chapter 8 |  |  | Janet Mayer |  | 19 | Fri | 2017-11-03
| Chapter 8 Review |  |  | Distribution List (Standards Committee) |  | 17 | Thur | 2017-11-16
| Chapter 8 Review Comments Due |  |  | Distribution List (Standards Committee) |  | 16 | Wed | 2017-11-22
| Stakeholders Meeting to Discuss Chapter 8 |  |  | Stakeholders Group |  | 16 | Wed | 2017-11-22
| Meeting to Discuss Chapter 8 |  |  | Standards Committee |  | 16 | Thur | 2017-11-23
| Begin Chapter 8 Revision |  |  | Janet Mayer |  | 16 | Fri | 2017-11-24
| Revised Chapter 8 Review |  |  | Distribution List (Standards Committee) |  | 14 | Thur | 2017-12-07
| Revised Chapter 8 Review Comments Due |  |  | Distribution List (Standards Committee) |  | 13 | Wed | 2017-12-13
| Meeting to Approve Chapter 8 and Look Ahead to Chapter 9 |  |  | Standards Committee |  | 13 | Thur | 2017-12-14
| Begin Chapter 9 |  |  | Janet Mayer |  | 13 | Fri | 2017-12-15
| Chapter 9 Review |  |  | Distribution List (Standards Committee) |  | 11 | Thur | 2017-12-28
| Chapter 9 Review Comments Due |  |  | Distribution List (Standards Committee) |  | 10 | Wed | 2018-01-03
| Stakeholders Meeting to Discuss Chapter 9 |  |  | Stakeholders Group |  | 10 | Wed | 2018-01-03
| Meeting to Discuss Chapter 9 |  |  | Distribution List (Standards Committee) |  | 10 | Thur | 2018-01-04
| Begin Chapter 9 Revision |  |  | Janet Mayer |  | 10 | Fri | 2018-01-05
| Revised Chapter 9 Review |  |  | Distribution List (Standards Committee) |  | 8 | Thur | 2018-01-18
| Revised Chapter 9 Review Comments Due |  |  | Distribution List (Standards Committee) |  | 7 | Wed | 2018-01-24
| Meeting to Approve Chapter 9 |  |  | Standards Committee |  | 7 | Thur | 2018-01-25
| Begin Compilation of Complete Standards |  |  | Janet Mayer |  | 7 | Fri | 2018-01-26
| Complete Standards Review |  |  | Distribution List (Standards Committee) |  | 5 | Thur | 2018-02-08
| Complete Standards Review Comments Due |  |  | Distribution List (Standards Committee) |  | 4 | Wed | 2018-02-14
| Stakeholders Meeting to Discuss Chapter 9 |  |  | Stakeholders Group |  | 4 | Wed | 2018-02-14
| Meeting to Discuss Compiled Standards |  |  | Standards Committee |  | 4 | Thur | 2018-02-15
| Compiled Standards Revision |  |  | Janet Mayer |  | 4 | Fri | 2018-02-16
| Revised Compiled Standard Review |  |  | Distribution List (Standards Committee) |  | 2 | Thur | 2018-03-01
| Revised Compiled Standards Review Comments Due |  |  | Distribution List (Standards Committee) |  | 1 | Wed | 2018-03-07
| Meeting to Approve Compiled Standards |  |  | Standards Committee |  | 1 | Thur | 2018-03-08
| Final Standards Complete |  |  |  |  | 0 | Thur | 2018-03-15
| Standards Completion Date |  | 2018-03-15
Formulas:
Deadline = (D111-(([Prior To]-1)*7)-6)