## Sheet1
Comment No. | Page/Section | Reviewer | Reviewer's Comment | Response | Response By
1 | 1/1.1 | HWD | Recommend changing language to "City capital improvement project" | Will delete "when so required by the City" | JMM
2 | 1/1.1 | Steve Beck | Add "except private roads being repaired or vested roads" at the end of 1st paragraph. | Not added, private roads are covered by Standards | JMM
3 | 1/1.1 | Steve Beck | Add "repaired roads or vested roads are exempt" at the end of second paragraph. | Not added, these would not be exempt | JMM
4 | 1 / 1.1 | Kent Ng | Third paragraph. In the first sentence, it mentions "utility pole and other utility structures…". In the last sentence, it only states "utility pole and other structures…". Suggest to revise one of these sentence for consistency. | Delete third paragraph, add "utilities" to second paragraph | JMM
5 | 2/1.3 | Steve Beck | For definition of Critical Areas, remove words "unique, fragile and other organisms". | Cannot change, this definition is the one used in SeaTac City Code | JMM
6 | 2/1.3 | Steve Beck | For definition of CSBC, remove words "crushed surfacing". | This is terminlogy used in WSDOT Standard Specifications, cannot change | JMM
7 | 2/1.3 | Steve Beck | For definition of CSTC, remove words "crushed surfacing". | This is terminlogy used in WSDOT Standard Specifications, cannot change | JMM
8 | 3/1.3 | Steve Beck | For definition of Design Speed, replace "highway" with "street". | Change to "roadway" | JMM
9 | 3/1.3 | Steve Beck | For definition of LID, remove definition, replace with "Local Improvement District". | For these standards, the reference is to "Low Impact Development" | JMM
10 | 4/1.3 | Steve Beck | A question mark (highway) next to the definition of Recoverable Slope. | This definition may not be used, we will revisit definitions after standards are complete | JMM
11 | 4/1.3 | HWD | Right-of-way - as defined, "any property that the city has any form of ownership or title for public road purposes"…would this apply to a parking lot, access to a park, city hall, etc. as it is maintained for public travel? Is there a definition of public road purposes? | City will research for best definition and change | JMM
12 | 4/1.3 | Steve Beck | For definition of Utility, add "stormwater" to list. | Will add stormwater to list and remove power, heat and light | JMM
13 | 5/1.4 | HWD | The applicability of the section is questionable in the road standards. This section if from a WSDOT spec for Capital contact work, it does not have applicability for say, Developer driven work. There are several words not defined (Contract, Contractor, Work). Consider a brief statement of the authority of the Engineer stating they have authority of all work within the City ROW. | This section will be revised and moved to Chapter 9 | JMM
14 | 5 / 1.4 | Kent Ng | First paragraph, fifth line, consider to change the word "challenge" to other words, such as "appeal". The last sentence states " provided in such cases un Washington case law." Suggest to clarify the word "un". | This section will be revised and moved to Chapter 9 | JMM
15 | 5 / 1.4 | Kent Ng | Suggest to include "deviation" to the bullet list. | This section will be revised and moved to Chapter 9 | JMM
16 | 5 / 1.4 | Kent Ng | First paragraph after the bullet list, second sentence states: "….or orders from the Engineer;" suggest to clarify written or verbal or both. | This section will be revised and moved to Chapter 9 | JMM
17 | 5 / 1.4 | Kent Ng | Next to the last paragraph. This paragraph references to WSDOT Standard Specs. Section 1-08.6. Suggest to have the City adopts your own ordinance or specifications related to "suspend Works" or stated the revision of the WSDOT Standard Spec. If WSDOT revises their standard specs., the City may have to issue revision to your Standard. | This section will be revised and moved to Chapter 9 | JMM
18 | 5 / 1.4 | Kent Ng | Could not understand the last paragraph. Is this paragraph talking about means and methods? | This section will be revised and moved to Chapter 9 | JMM
19 | 6 /1.5 | HWD | Second paragraph is based from WSDOT spec and may not be applicable for Developer work. | This section will be revised and moved to Chapter 9 | JMM
20 | 6 / 1.5 | Kent Ng | First paragraph, needs to clarify who is "appoint assistants and "Inspectors." Are these staff considers as City employees or consultants? | This section will be revised and moved to Chapter 9 | JMM
21 | 6 / 1.5 | Kent Ng | Assume the City has not developed the language for this Section. And there is not section title for 1.6 | This section will be revised and moved to Chapter 9 | JMM
22 | 6 / 1.5 | Kent Ng | Second paragraph, if the Assistants/Inspectors are not authorized to accept Work, needs to clarify the process and personnel who can accept Work. | This section will be revised and moved to Chapter 9 | JMM
23 | 6 /1.5 | HWD | We have had previous concerns in the past about inspector driven instructions and the applicability/authority to direct the work which is contrary with this language in the second paragraph. | This section will be revised and moved to Chapter 9 | JMM
24 | 6 /1.5 | Steve Beck | First sentence, add "private, non-City" after appoint. | This section will be revised and moved to Chapter 9 | JMM
25 | 6/1.6 A | Steve Beck | First sentence, add "authorized study" after City code. | Need to ask Steve what the intent of comment is | JMM
26 | 6/1.6 B | Steve Beck | Second sentence, add "or authorized study" at the end of sentence. | Need to ask Steve what the intent of comment is | JMM
27 | 6/1.6 F | Steve Beck | End of second sentence add "unless otherwise approved by the director. | Not added, may lead to inconsistencies | JMM
28 | 6 / 1.6 | Kent Ng | Bullet A., needs to clarify who and when the off-site roadway improvements were established. | Section 1.6 will be revisited by the Standards Committee - is this section necessary or does it need more details? | JMM
29 | 6 / 1.6 | Kent Ng | Bullet A., suggest to include discussion about the limit to improve the frontage. | Section 1.6 will be revisited by the Standards Committee - is this section necessary or does it need more details? | JMM
30 | 6 / 1.6 | Kent Ng | Bullet E., should Road Classifications, instead of Urban Characteristics, determine the type of road improvement? How about illumination? | Section 1.6 will be revisited by the Standards Committee - is this section necessary or does it need more details? | JMM
31 | 7 /1.6 G | Steve Beck | End of sentence add "or Director". | Section 1.6 will be revisited by the Standards Committee - is this section necessary or does it need more details? | JMM
32 | 7 / 1.6 | Kent Ng | Bullet G, needs to clarify which standard requires what types and limits of pedestrian and bicycle improvements. | Section 1.6 will be revisited by the Standards Committee - is this section necessary or does it need more details? | JMM
33 | 7 / 1.6 | Kent Ng | Suggest to discuss road restoration, such as half street improvements, overlay, pavement limits. | Section 1.6 will be revisited by the Standards Committee - is this section necessary or does it need more details? | JMM
34 | 7 /1.9 | Steve Beck | Add to end of sentence "except when exempt by code or Dept. Mgr." | Need clarification from Steve | JMM
35 | 7 / 1.9 | Kent Ng | How about King County Surface water design manual and King County Road Standard? | King County Water Design manual is on list, we will not be referencing the King County Road Standards | JMM
36 | 9 /1.10.B.1.h | Steve Beck | Third sentence, add "unless otherwise waived by the Director" after within the project. | Not added, may lead to inconsistencies | JMM
37 | 9 /1.10.B.3.b | Steve Beck | Why only WSDOT Standard Plans? | If there is not a standard detail/plan provided in these standards for an item, then we default to WSDOT standard details/plans. | JMM
38 | 9 /1.10.C.1 | Steve Beck | Replace 2,000 with 5,000. King County Standards on small lot BMP's & others. | Ali Shasti will research this item | JMM
39 | 9 /1.10.C.3 | Steve Beck | Add to end of sentence "or is exempt under the SWM Manual". | Janet will discuss this with Don Robinett (Stormwater Compliance Manager) | JMM
40 | 10 / 1.11 | Kent Ng | Consider to change the word "superimpose" to "any modifications in red line" on top of approved design documents - drawings and specifications. | This will be discussed by Standards Committee - specify that record drawings are not required for franchise facilities. | JMM
41 | 10 / 1.11 | Kent Ng | Bullet A. 1., suggest to include specifications. | Not all projects need to have specs, so we will not include this | JMM
42 | 10 / 1.11 | Kent Ng | Sample drawings will really help. | They are currently in development | JMM
43 | 10 / 1.11 | Kent Ng | Consider to include driveway plan and profile. | This will be on a project by project basis, will not include in standards | JMM
44 | 11 /1.12.A | Steve Beck | At end of sentence add "and/or benefits the project from an environmental & common sense standards. | Not incorporated | JMM
45 | 11 / 1.12 | Kent Ng | Suggest to develop Deviation Form. | CED has developed a form that will most likely be used, or will modify the WSDOT form | JMM
46 | 11/1.12.D | Steve Beck | Not feasible was underlined, comment added "monetarily or construction design". | See resolution to comment #48 | JMM
47 |  | Earl Gipson | Once the document is entirely completed, how will revisions be controlled, reviewed, and publicized? Will these be internal to the City only (admistrative)? Will there be periodic review? | This needs to be addressed, will be discussed at Standards Committee meeting | JMM
48 |  | HWD | Recommend providing an appeal process to directions/review of the Development Review Manager or City Engineer to the Planning Director and or Public Works Director, and then if required the Council. This is an important step to ensure consistency with reviews and interpretation of these standards | Yes, a reference to the City code which details the appeal process will be added | JMM
49 | 1/1.1 | Ali Shasti | Remove "within the City right-of-way at the end of 1st paragraph. | Will remove | JMM
50 |  | HWD | Add hierarchical order for contract documents | Will add | JMM